## Revenue
Status of Funding Transfer Station improvements - April 2024
Income |  |  | Amount Appropriated in WA #12 | Accumulated Cash | Interest Earned | Funds Used | Remaining Cash Funds | Anticipated Cash | Anticipated Grant | Total Remaining Resources as of Feb. 2024 | Notes
Grants
|  | USDA Grant Awarded May 2022 | 493570 | [5 empty] | 493570 | 493570 | Granted, and is a reimbursable Grant - and used only for last third of project, thus no funds are in Town of Tamworth Accounts.
|  | Tamworth Foundation - Awarded March 2022 | 125000 | 125000 | 6734.1 |  | 131734.1 |  |  | 131734.1
|  | ARPA Funds (Previously approved & Spent - 2021/2) |  | 18606 |  | 18605 |  |  |  | 0 | Funding for Well construction & Drilling, Septic design,Septic Tank purchase
|  | ARPA Funds Voted for Transfer Station Improvement | 100000 | 100000 |  |  | 100000 |  |  | 100000 | 12/29/22 Select Board Meeting Vote
[7 empty] | 0 |  |  | 0
| Capital Reserve: | [5 empty] | 0 |  |  | 0
|  | 2021 WA #9, $100,000: $64k from the Unexpended Fund Balance and $36k from taxation. | 93250 | 93250 | 6634.93 | 6750 | 93134.93 |  |  | 93134.93 | $6,750 spent on USDA required Environmental Report
Warrant Article #12, 2022 Town Meeting Vote, $274,460 per year**
|  | 2022 Voted ($125,000 came from Tam Foundation - See above) | 149460 | 149460 |  |  | 149460 |  |  | 149460 | $50,000 From Unassigned Fund Balance voted in each of Three Years
|  | 2022 Voted for 2023 ($100K from ARPA - See Above) | 174460 | 174460 |  | 122737 | 51723 |  |  | 51723 | $50,000 From Unassigned Fund Balance voted in each of Three Years
|  | 2022 Voted for 2024 | 274460 | 274460 |  |  | 274460 |  |  | 274460 | $50,000 From Unassigned Fund Balance voted in each of Three Years
0
Total Income Actual |  |  | 1410200 | 935236 | 13369.03 | 148092 | 800512.03 | 0 | 493570 | 1294082.03

## Expenses
Transfer Station Costs
Vendor | Purpose | Amt. | Status | Check # | Notes
HEB | USDA Required Environmental Study | 6750 |  |  | Paid for out of Capital Reserve pre 2022 Vote.
GW Brooke | Septic Tanks for Transfer Station (in storage) | 5710 | Paid | 44721 | Paid for with ARPA Funds
Hartley | Well construction - Transfer Stn. | 10395.61 | Paid | 44561 | Paid for with ARPA Funds
Colbot | Designs for both Well | 650 | Paid | 44676 | Paid for with ARPA Funds
McConkey | Transfer Septic Design | 1850 | Paid | 44497 | Paid for with ARPA Funds
Sanborn Head | Engineering Asssesment - 2023 work | 122737 | Paid |  | Paid for out of TSIC Funds
Transfer Sub Total |  | 148092.61
Purchasing costs
| Testing Soil | 50000 |  |  | Possible grant form LRPC
| Sanborne Head//Engineering for operations | 50000
| Moving Costs | 20000
building renovations
| Eye Wash Station | 10000
| Compactor arrangement | 150000
| Misc Equip | 200000
|  | 480000 |  |  | What is commercial rental market
Operating costs
| Operation of the Office building | 15000 |  |  | Realtor for current operating costs /heating electric